## Gantt chart1
Task | Assigned To | Start Date | End Date | Duration
Make Gantt Chart | Everyone | 2015-03-24 | 2015-03-25 | 1 | Done
Find our API | Alex | 2015-03-25 | 2015-03-26 | 1 | Done
Determine Languages for Difficulty Levels | Otis and his boy, Alex | 2015-03-26 | 2015-03-29 | 3 | Done
Design the GUI | Otis | 2015-03-29 | 2015-03-31 | 2 | Done
Name the Game | Preston | 2015-03-25 | 2015-03-26 | 1 | Done
Code the Program | Everyone | 2015-03-26 | 2015-04-17 | 22
Figuring out the API | Kira | 2015-03-26 | 2015-03-30 | 4 | Done
Psuedo-code | Preston | 2015-03-26 | 2015-03-28 | 2 | Done
Code it based on Psuedo-code | Everyone | 2015-03-31 | 2015-04-17 | 17
Spring Break | Everyone | 2015-04-01 | 2015-04-08 | 7
Testing | Everyone | 2015-04-17 | 2015-04-29 | 12
System Test | Everyone | 2015-04-17 | 2015-04-18 | 1
Bug Test | Everyone | 2015-04-18 | 2015-04-20 | 2
Bug Fixes | Everyone | 2015-04-20 | 2015-04-23 | 3
Final Test | Everyone | 2015-04-23 | 2015-04-24 | 1
Final Fixes | Everyone | 2015-04-24 | 2015-04-26 | 2
Playtesting | Everyone | 2015-04-26 | 2015-04-29 | 3
Final Release | Everyone | 2015-04-29 | 2015-04-30 | 1
Gantt Chart made by Everyone
Formulas:
End Date = [Start Date]+[Duration]
Start Date = [End Date, row above]

## Gantt chart2
Task | Assigned To | Start Date | End Date | Duration
Task 1 |  | 2014-04-01 | 2014-05-31 | 60
Task 2 |  | 2014-06-01 | 2014-08-05 | 65
Task 3 |  | 2014-08-06 | 2014-08-28 | 22
Task 4 |  | 2014-08-29 | 2014-10-14 | 46
Task 5 |  | 2014-10-15 | 2014-10-26 | 11
Task 6 |  | 2014-10-27 | 2014-12-06 | 40
1899-12-31
Formulas:
End Date = [Start Date]+60
Start Date = [End Date, row above]+1